| MINISTRY OF SCIENCE & TECHNOLOGY No.: 528/QD-BKHCN | SOCIALIST REPUBLIC OF VIETNAM Independence – Freedom – Happiness Ha Noi, March 15, 2018 |
| --- | --- |

DECISION

Approving the organization plan for the Program on “Science and Technology for Agricultural Development in the South Central Coast and Central Highlands 2018”

MINISTER OF SCIENCE AND TECHNOLOGY

Pursuant to the Government’s Decree no. 95/2017/ND-CP issued on August 16, 2017 specifying the functions, tasks, powers and organization structure of the Ministry of Science and Technology;

According to the suggestion of Director of the National Agency for Technology Entrepreneurship and Commercialization Development,

DOES HEREBY DECIDE:

Article 1. Approving the organization plan for the Program on “Science and Technology for Agriculture Development in the South Central Coast and Central Highlands in 2018” enclosed with this Decision.

Article 2. Director of the National Agency for Technology Entrepreneurship and Commercialization Development, Director of Vietbrand Center for Research, Application and Development, members of the Organization Board and relevant agencies shall have follow this Decision.

| Copies to: - As Article 2; - Minister (for reporting); - Kept in the archives, National Agency for Technology Entrepreneurship and Commercialization Development. | SIGN FOR MINISTER DEPUTY MINISTER (Signed and sealed) Tran Van Tung |
| --- | --- |

ORGANIZATION PLAN FOR THE PROGRAM ON “SCIENCE AND TECHNOLOGY FOR AGRICULTURAL DEVELOPMENT IN SOUTH CENTRAL COAST AND CENTRAL HIGHLANDS 2018”

(Promulgated with the Decision no. 528/QD-BKHCN dated March 15, 2018)

I. The necessity

Agriculture has become an important economic sector for socioeconomic development, provided significant benefits and practical economic effectiveness, and greatly contributed to the state budget. The Party and the State have also identified agriculture, farmers and rural areas as strategic roles in the national construction and defense. To implement the Party’s innovation policies and the 11th National Party Congress Resolution, the agriculture sector has concretized this Resolution by initiating many Programs, Projects, Plans and focused on conducting the following contents: agricultural restructure by improvement of the added values and sustainable development; National Target Program on New Rural Construction; and application of advanced technologies for agricultural development. Besides, pursuant to the Resolution no. 01 / NQ-CP dated January 1, 2017 concerning major missions and solutions for directing and administering the implementation of socioeconomic development plans and state budget estimates in 2017, many  major missions and solutions for implementing the socio-economic development plans have been proposed such as “Offering preferential mechanisms and policies; creating a favorable environment for agricultural cooperatives to develop; facilitating businesses to invest in rural development, especially startups of agriculture, hi-tech agricultural development, agriculture adaptation to climate change; perfecting the legal framework for encouraging connections in agricultural production; researching, transferring and applying science and technology for agricultural production to reach a clean, high-tech and environmentally-friendly agriculture”.

The South Central Coast and Central Highlands have favorable geological positions and a short distance from Ho Chi Minh City and key economic triangle. Therefore, these conditions are good for such cities and provinces as Da Nang, Quang Nam, Quang Ngai, Binh Dinh, Phu Yen, Khanh Hoa, Ninh Thuan, Binh Thuan, Dak Lak, Dak Nong, Gia Lai, Kon Tum and Lam Dong to produce agricultural and forestry products and contribute to the regional socioeconomic development. According to the guidelines of the Party and the State regarding agricultural and rural development, high technology agriculture as well as application of scientific and technological achievements for agricultural development in the new era, the Program on Science and Technology for Agricultural Development in the South Central Coast and Central Highlands 2018 is very suitable and meaningful for introducing and commercializing agricultural technologies and products in Vietnam. Details of the Program are shown below:

1. Exhibition: Introducing and displaying agricultural technologies, equipment and products that have been successfully invested and researched by businesses, cooperatives and farming households from all cities and provinces of Vietnam and by foreign businesses.

2.  Conference on “Scientific and Technological Application for Agriculture”: Exchanging experience in successfully applying scientific and technological achievements and intensifying the cooperation between both local and foreign scientists, investors and businesses.

3. Program on “Investment Matching and Technological Transfer”: Matching institutes, universities and scientists with businesses, cooperatives and farming households to promote technological innovation and transfer and scientific and technological application for agricultural business and production as well as linking to prestigious suppliers, experts and consultants to get appropriate preferential policies.

4. Program on “Agriculture – Craft Village Extension”: Diffusing agricultural cultivation, organic agricultural production and clean agricultural models carried out by Vietnam businesses, cooperatives and farming households.

5. Program on “Introduction and Presentation of Technologies, Production Equipment and Technological Products”: Introducing technologies, equipment, processes and products concerning agricultural processing and storage offered by scientists and investors to all businesses, cooperatives and farming households.

II. Organization plan

1. Time and place:

- Time: 28/6/2018 to 01/7/2018 (4 days).

- Place: Thanh Nien Stadium, Tran Phu Street, Nha Trang City, Khanh Hoa Province

2. Governing body and relevant agencies

a) Governing/directing body: Ministry of Science and Technology

b) Relevant agencies:

- People’s Committee of Khanh Hoa Province;

- Ministry of Agriculture and Rural Development;

- Ministry of Industry and Trade

- People’s committees of provinces/cities in the South Central Coast and Central Highlands;

- National Agency for Technology Entrepreneurship and Commercialization Development

- Vietbrand Center for Research, Application and Development – Vietnam Union of Science and Technology Associations;

- Vietbrand Electronic Communication Network.

3. Program details

a) Part 1: Displaying agricultural technologies, equipment and products

- 300 – 500 booths of local and foreign businesses, cooperatives and farming households that have applied scientific and technological achievements for agricultural production.

- Time and place:

+Time: 28/6/2018 to 01/7/2018 (04 days).

+Location: Thanh Nien Stadium, Tran Phu Street, Nha Trang City, Khanh Hoa Province

- Organization Board: Vietbrand Center for Research, Application and Development; National Agency for Technology Entrepreneurship and Commercialization Development; National Office in Southern Region; and Vietnam Trade Promotion Agency – Ministry of Industry and Trade.

b)Part 2: Conference on “Scientific and Technological Application for Agriculture”

- Time: 8:00 a.m. – 12:30 p.m. on 29/06/2018.

- Location (proposed): Khanh Hoa Conference Center.

- Governing body: Ministry of Science and Technology; representative of Ministry of Agriculture and Rural Development; and leaders of People’s Committee of Khanh Hoa Province.

- Attendance: 200 – 300 people.

- Organization Board: National Agency for Technology Entrepreneurship and Commercialization Development, Vietbrand Center for Research, Application and Development.

c) Part 3: Program on “Investment Matching and Technological Transfer”

- Time: 8:30 a.m. on 30/06/2018.

- Location (proposed): Khanh Hoa Conference Center.

- Attendance (proposed): 60 – 80 businesses.

- Organization Board: Vietbrand Center for Research, Application and Development, National Office in Southern Region - Ministry of Science and Technology

d) Part 4: Program on “Agriculture – Craft Village Extension”

- Time: 2:00 p.m. to 5:00 p.m. on 29-30/06/2018 (2 sessions).

- Location: Farms, enterprises and craft villages of businesses, cooperatives and farming households.

- Attendance: 80 - 100 people

- Organization board: Vietbrand Center for Research, Application and Development; Khanh Hoa Agricultural Extension Center

e) Part 5: Program on “Introduction and Presentation of Technologies, Production Equipment and Technological Products”

Time: 30/06 - 01/07/2018 (2 sessions)

Location: Exhibition center

Attendance: 100-150 people (businesses, cooperatives, farmer  households).

Organization board: Vietbrand Center for Research, Application and Development; relevant agencies.

III. Detailed schedule (as proposed)

| No | Time | Content | Attendance |
| --- | --- | --- | --- |
| 1 | June 28, 2018 7:30 p.m. – 9:00 p.m. | Live broadcasting * Opening ceremony - Music performance - Introduction - Opening speech by the head of the Ministry of Science and Technology - Welcome speech by Chairman of the People’s Committee of Khanh Hoa Province - Congratulatory speech by the representatives of the Party and State | Representatives of the Party and State; Leaders of the Ministry of Science and Technology; Head Leaders of the Ministry of Agriculture and Rural Development; Leaders of the Ministry of Industry and Trade; Leaders of the people’s committees of cities and provinces in the South Central Coast and Central Highlands; Central and local departments, bodies, press agencies, radio and TV stations; Businesses, cooperatives and farming households. |
| 2 | June 29, 1818 8:00 a.m. – 12:00 noon | Conference on “Scientific and Technological Application for Agriculture” | Leaders of the Ministry of Science and Technology ; Representatives of the Ministry of Agriculture and Rural Development ; Representatives of the Ministry of Industry and Trade; Leaders of the people’s committees of cities and provinces ; Scientists, central and local press agencies, radio and TV stations ; Businesses, cooperatives and farming households. |
| 3 | June 30, 2018 8:30 a.m. – 12:00 noon | Program on “Investment Matching and Technological Transfer” | Representatives of the Ministry of Science and Technology ; Representatives of local departments and bodies; Representatives of institutes and universities and scientists; Representatives of press agencies, radio and TV stations ; Businesses, cooperatives and farming households . |
| 4 | June 29-30, 2018 2:00 p.m. – 5:00 p.m. | Program on “Agriculture – Craft Village Extension” | Representative of the Organization Board Place: farms, enterprises and craft villages of businesses, cooperatives and farming households Representatives of institutes and universities and scientists Businesses, cooperatives and farming households. |
| 5 | June 30 – July 1, 2018 1:30 p.m. – 5:00 p.m. | Program on “Introduction and Presentation of Technologies, Production Equipment and Technological Products” | Representatives of the Organization Board Place: Exhibition center Attendance: 100 – 150 people (businesses, cooperatives and farming households ) |

III. Entertainment and communication activities

1. Entertainment:

-  Music and comedy performances held every night for all guests and visitors;

-  Traditional cuisine for all guests and visitors.

2. Communication:

-  Live broadcasting on National Assembly TV, Khanh Hoa TV or VTV9;

-  Southern press agencies, radio and TV stations;

-  Popularizing details of program items to all regions of Vietnam.

IV. Expenses

Expense sources:

- Reciprocal expenses from permanent activities of Vietbrand Center for Research, Application and Development;

- Socialization expenses.

- Expenses from other lawful sources.